## Slide 1
ZERO TO HERO · IDEA TO APP
Team Roles &
Workstreams
June 2025 | Action Items · M1 To-Do · Process Flow · Welcome Email · Roles & Responsibilities · Workstreams · Dependencies · Phase Cards · Cadence · GitHub Guide
COLOUR KEY:
Munish
Shefali
Hansh
Eddie
Yash
TBD
Each colour identifies one person consistently across all slides in this deck.

## Slide 2
ACTION ITEMS — JUNE 9 GROUP MEETING
Action Items — June 9 Group Meeting
Tasks agreed at the first full team meeting. Status reflects current state as of June 10.
OWNER
ACTION ITEM
WHEN
STATUS
Eddie
Confirm Om Maheshwari: interest and availability for editing and/or music role. Report back to Munish.
M1 Wk1
Pending
Munish
Add Yash's suggestion: highlight individual contributions and value received from cohort members in the documentary questionnaire.
M1
Pending
Munish
Reach out to Sagar Batra (content/event marketing) and Om Maheshwari (music) as roles are confirmed and when ready.
M1
Pending
Shefali
Mentor/transfer Project Manager (PM) responsibilities to a detail-oriented team member. Shefali is temp PM.
M2
Pending
Shefali
Simplify the playbook into a deck so it is easily digestible for the whole team.
M1
✓ Done
Munish +
Shefali
Update Roles & Responsibilities from June 9 meeting decisions.
M1
✓ Done
Yash
Take ownership of marketing/distribution role. Coordinate with Munish on content. Begin planning social media and promotional activities.
M1
Pending
All
Review the playbook. Clarify and accept roles. Inform Munish of any role changes or additional support needs.
M1 Wk1
Pending
All
Be diligent in organising and naming all documentary footage as it is collected. Follow folder structure and best practices in the playbook.
Ongoing
Pending
All
Legal and branding: do not reference '100X' publicly. Use 'learning community'. Shefali's guidance.
Ongoing
Pending

## Slide 3
ACTION ITEMS — JUNE 9 POST-MEETING (SHEFALI + MUNISH BILATERAL)
Action Items — June 9 Post-Meeting
Decisions from the Shefali + Munish session after the group meeting.
OWNER
ACTION ITEM
WHEN
STATUS
Shefali
Send questionnaire to all 30 ACES members. Participants self-select: tick a box if they want to be a protagonist. Shortlist 5 from responses.
M1 Wk1
Pending
Shefali
Create and distribute protagonist selection rubric (scores on specificity, emotional stakes, contrast potential, surprise factor).
M1 Wk1
✓ Done
Shefali
Retain Project Manager (PM) role for now. Identify and begin mentoring a detail-oriented second person for PM. Not urgent until M2.
M2
Pending
Shefali
Begin outreach to find an Indian entertainment lawyer or advisor. Not needed until M3+. Do not use '100X' publicly — use 'learning community'.
M3+
Pending
Eddie
Confirm with Om Maheshwari: interest in editing and/or music role. Om sits as sub-role under Eddie's or Hansh's workstream.
M1 Wk1
Pending
Munish
Reach out to Sagar Batra for content/event marketing sub-role under Yash's workstream when ready.
M1
Pending
Munish
Decide budget ownership: Hansh, Shefali, or future Producer? This is blocking the budget line in the playbook.
M1
Pending
Munish
Clarify Exec/Producer definition with Shefali before Netflix pitch. Not blocking immediate production.
M2
Pending
Hansh
Set up GitHub repository and full folder structure before M2 filming begins. Nothing gets filmed until this system exists.
M1 Wk1
Pending
All
Weekly async update to GitHub README by each workstream owner every Friday. WhatsApp for urgent decisions only. Bilateral Zoom if thread exceeds 5 messages.
Ongoing
Pending

## Slide 4
ROLES & RESPONSIBILITIES — v3.0 | JUNE 9, 2025
Roles & Responsibilities
Colour = person. Consistent across all slides in this deck.
TITLE(S)
NAME
WHAT THEY OWN
WHERE TEAM CROSS-SUPPORTS THEM
Director
Munish Bhardwaj
Creative vision, story direction, picture lock, Netflix relationship, music sign-off, weekly meeting chair, tiebreaker on all decisions.
Shefali manages scheduling. Director reviews footage.
Showrunner / Narrator /
Story Producer / PM (temp)
Shefali Mody + Eddie
Questionnaire to all 30 (M1). Zoom interviews of the 5 selected protagonists (with Eddie). Weekly prompts. Character arc & story bible. All Project Manager (PM) duties. Cut review coordination.
Munish owns all editorial. Eddie/Munish & Shefali review initial content.
Director of Photography
Eddie Bhardwaj
Hardware tech — call to understand each protagonist's working environment. Camera angles to record. Settings for same footage from different angles.
Shefali briefs on story priorities. Hansh provides ingest system.
Post Production
(+ Om Maheshwari)
Hansh Goyal
Editing, file video, WhatsApp archive, archival footage, storage & categorisation, sound effects & motion capture, budget tracking, colour grade, sound mix, Netflix delivery.
Shefali & Eddie view and categorise content.
Marketing & Content Strategist,
Music Brief Owner
(+ Sagar Batra)
Yash Javeri
Hardware audit of all 30. Screen recording & Zoom setup guide. Social media presence. Content calendar. Weekly publishing M3–M6. Music brief co-owner. Release & distribution strategy co-owner.
Hansh provides ingest system. Munish approves all public-facing content.
Exec/Producer
TBD
Budget. Face of documentary pitches. (Needs more clarity around this role definition.)
—
Music / Audio Design
TBD
Final say on sound of documentary. B-tracks. Scale. Sound effects. Ambient music. Must resolve before M5 (Aug–Sep).
—
Budget
TBD
Legal advisor coordination. Financial tracking.
—
Legal
TBD
Indian entertainment lawyer or advisor. Not needed until M3 (August).
—
⚠ STILL UNRESOLVED — needs owner before production begins

## Slide 5
TEAM CADENCE RECOMMENDATION
Team Cadence Recommendation
Replacing Chapter 24. The team wants async — here's how to make it work.
Fully Async
GitHub + WhatsApp only
Pros
Fits distributed volunteer team
No scheduling stress
Lower overwhelm
Cons
Decisions go cold fast
Munish's creative direction at risk
People Operations PM load increases
Weekly Sync
Current Playbook (Ch. 24)
Pros
Decisions made fast
Creative direction protected
Single alignment point
Cons
Hard to schedule across time zones
Volunteer team resists it
Team called it overwhelming
✓ Recommended
Async-first + Bi-weekly Check-in
Pros
No weekly sync
Bi-weekly 30-min check-in / stand-up (Munish chairs)
Weekly async README update by each workstream owner
WhatsApp for urgent decisions only
Bilateral Zoom if thread exceeds 5 messages
Cons
Requires discipline on README updates
Bi-weekly check-in is a hard commitment — no skipping

## Slide 6
SUB-TEAM MEMBER SELECTION RUBRIC
Sub-Team Member Selection Rubric
Skills, not just enthusiasm. Use when any workstream lead recruits — Om Maheshwari, Sagar Batra, or anyone else.
1. Relevant Skill
Does this person have a demonstrable skill the workstream actually needs? Not 'I've always wanted to try editing' — evidence of actual capability. Ask for examples or work samples.
0–5
2. Availability
Can they genuinely commit to async deliverables each week? Volunteer enthusiasm fades. Probe actual weekly hours available, not aspirational ones.
0–5
3. Async Discipline
Do they respond to messages? Do they follow through without being chased? One data point: have they delivered on anything in the cohort so far?
0–5
4. Alignment with Tone
Do they understand this is a real documentary, not a side project? Do they respect the participants' stories? Check for seriousness of intent.
0–5
5. Workstream Fit
Does their skill fill a specific gap in the workstream? Score higher if they complement (not duplicate) what the lead already does.
0–5
Shortlist anyone scoring 18+ · Pass at 12 or below · Discuss 13–17 with Munish before deciding

## Slide 7
M1 PROCESS FLOW — JUNE 2025
M1 Process Flow — June 2025
The sequence within Month 1. Each step is a dependency for the next. Colour = person responsible.
1
Welcome Email
sent to all 30
2
Questionnaire
to all 30 ACES
3
GitHub repo
set up + live
4
Responses
reviewed + shortlist
5
5 protagonists
selected
6
Consent forms
signed (5 only)
7
Protagonist
onboarding
8
DOP calls
each protagonist
9
Interview Qs
prepared & approved
10
Zoom interviews
5 protagonists only
11
Budget decision
owner confirmed
← Weeks 1–2 →
← Weeks 2–3 →
← Week 4 →
COLOUR KEY:
Munish
Shefali
Hansh
Eddie
Yash
A
Social Marketing Campaign Plan and Launch
Shefali/ Eddie

## Slide 8
M1 (JUNE) TO-DO LIST — SYNTHESISED FROM BOTH MEETINGS | DO THESE IN ORDER
M1 To-Do List — June 2025
Not a new list — the action items from both meetings, sequenced by dependency. Each item must be done before the next begins.
OWNER
ACTION ITEM
WHEN
STATUS
Shefali
Finalise and send Welcome Email to all 30 ACES members. Include the link to the questionnaire. (Email template on next slide.)
Wk 1
Pending
Shefali
Send questionnaire to all 30. Participants self-select protagonist interest by ticking a box. Collect all responses.
Wk 1
Pending
Hansh
Set up GitHub repository. Create folder structure. Add README with workstream sections and Friday update format. Share access with all 5 team members.
Wk 1
Pending
Munish +
Shefali
Review all questionnaire responses together. Apply the selection rubric. Identify 5 protagonists.
Wk 2
Pending
Shefali
Send consent forms to the 5 selected protagonists. Simple sign-off only — no legal review needed at this stage.
Wk 2
Pending
Shefali
Schedule and run protagonist onboarding session (group). Cover: what it means to be a protagonist, filming setup, hardware, what comes next.
Wk 3
Pending
Eddie
Begin DOP calls with each of the 5 protagonists. Understand their working environment. Camera angles, settings, lighting. Confirm hardware setup.
Wk 3
Pending
Munish +
Shefali
Draft protagonist story arc notes (informal). What do we expect from each person's arc? This informs the Zoom interview questions.
Wk 3
Pending
Shefali +
Eddie
Zoom interviews — the 5 selected protagonists only. Shefali leads. Eddie as second. These become the film's backbone.
Wk 4
Pending
Munish
Decide budget ownership: Hansh, Shefali, or future Producer? Make the call — this is blocking the budget line in the playbook.
Wk 4
Pending

## Slide 9
THE 5 WORKSTREAMS
The 5 Workstreams
Read your workstream. Colour = your person. Names match exactly across this deck and the Roles & Responsibilities slide.
Story &
Creative
Munish + Shefali
Narrative arc & story bible
Questionnaire (all 30 ACES)
Protagonist selection rubric
Weekly prompts (Shefali)
Cut direction & picture lock
People
Operations
Shefali + Eddie (PM temp)
Scheduling & participant comms
Consent forms (5 protagonists)
Protagonist onboarding
Zoom interviews — 5 only (Shefali + Eddie)
GitHub README updates
Content
& Post
Hansh (+ Om Maheshwari)
File system & naming
WhatsApp archive
Archival footage (ACES)
Colour grade & sound mix
Netflix delivery
Hardware
& Tech
Eddie (+ Om TBD)
DOP setup — call each protagonist
Camera angles & settings
Same footage from different angles
Screen recording guide
Graduation day camera
Marketing &
Distribution
Yash (+ Sagar Batra TBD)
Social media & content calendar
Weekly publishing from M3
Release & distribution strategy
Festival submissions
Hardware audit of all 30

## Slide 10
PHASE CARDS — JUNE TO SEPTEMBER 2025
Phase Cards — What Happens When
Compressed to real timeline. Celebration event target: mid-September.
M1
June
Development
Concept & Netflix pitch (Munish + Shefali)
Questionnaire to all 30 ACES (Shefali)
Consent forms, budget, music brief (Hansh + Munish)
GitHub repo + folder structure (Hansh)
Protagonist selection + onboarding
DOP calls begin (Eddie)
M2
July
Pre-Production
DOP setup complete — all protagonists (Eddie)
Questionnaire responses reviewed — shortlist 5
Zoom interviews — 5 protagonists only (Shefali + Eddie)
Protagonist story arc briefs (Munish + Shefali)
Content & social strategy live (Yash)
M3–M4
August
Production
Weekly prompts every Monday (Shefali)
Self-shot footage arriving (Hansh manages files)
WhatsApp archive daily (Hansh)
Weekly content publishing (Yash — Munish approves)
Story bible updated every Friday (Shefali)
M5
Aug–Sep
Post-Production
Paper edit → rough cut → fine cut (Om + Hansh)
Narrator script + recording if needed (Shefali)
Cut review feedback forms (Eddie + Munish)
Colour grade, sound mix (Hansh)
Music clearance (Munish)
M6 +
Event
September
Delivery + Celebration
QC + legal clearances (Shefali + Hansh)
Netflix submission (Munish + Hansh)
Marketing assets + release activation (Yash)
🎉 Celebration event — mid-September
Munish + Shefali sign off

## Slide 11
WORKSTREAM DEPENDENCIES — JUNE – SEPTEMBER 2025
Workstream Dependencies
Real months shown. Compressed to fit September celebration event. Outlined bars = active. Colour = lead person.
WORKSTREAM
June
M1
July
M2
August
M3–M4
Aug–Sep
M5 Post
Sep
Delivery
Mid-Sep
🎉 Event
Story &
Creative
Concept
+ pitch
Protagonist
selection
Story bible
+ prompts
Paper edit
+ narration
Sign off
People
Operations
Consent
+ onboard
Interviews
+ comms
Prompts
+ comms
Cut review
Legal
clearance
Content
& Post
File system
setup
Archive +
footage in
Edit + grade
+ sound
Netflix
delivery
Hardware
& Tech
DOP calls
+ setup
Recording
support
Event
camera
Marketing
& Distrib.
Strategy
+ setup
Content
strategy
Weekly
publishing
Build
audience
Release
launch
Event
promo
Key Dependencies:
File system (June M1) must exist before ANY footage is uploaded
DOP calls (July M2) must complete before protagonist recording begins
Protagonist selection (June) unlocks People Operations onboarding
Content & Post edit (Aug–Sep M5) depends on Story & Creative paper edit completing first
Music/Audio Design must be confirmed owner before M5 (Aug–Sep) begins

## Slide 12
WELCOME EMAIL — FOR REVIEW AND APPROVAL BEFORE SENDING
Welcome Email — For Approval
Sent by Shefali to all 30 ACES members, Week 1 of June. Peer-to-peer tone — not a formal production announcement.
FROM: Shefali Mody | TO: All 30 ACES members (BCC) | SUBJECT: Something we're building — and I need your help (5 min read)
Hi [Name],
I want to tell you about something that's happening alongside this program — and to ask if you'd like to be part of it.
I'm one of you. I'm in this cohort, doing this course, trying to build something with AI that I've never built before. And somewhere in the chaos of the first week I started thinking: this story is extraordinary. And somebody should capture it.
So we're making a documentary. Not a polished, corporate, 'here's-what-AI-can-do' documentary. A real one. About what it actually feels like to be a non-technical person thrown into a room with 29 strangers from around the world, all trying to learn something hard together, all secretly terrified, all somehow becoming each other's support system.
Munish Bhardwaj is directing it. He's also making a documentary for the first time — which, as you might appreciate, fits the theme perfectly.
Here's what I'm asking: a short questionnaire. Nothing technical. Just honest answers about where you are and what this means to you. At the end, you can say whether you'd like to be in the documentary — and whether you'd like to be considered as one of five protagonists we follow in depth. Both completely optional.
Takes about 15 minutes. No right answers. [LINK TO QUESTIONNAIRE]
Your answers are read by me and Munish only. You can opt out at any point, no questions asked.
With warmth and mild chaos,
Shefali — Showrunner / Narrator / Story Producer / Project Manager, and just like you, figuring it out as she goes.
ACTION REQUIRED: Munish to review and approve this email before Shefali sends. Reply with any changes.

## Slide 13
ALL-30 QUESTIONNAIRE — FOR REVIEW AND APPROVAL BEFORE SENDING
All-30 Questionnaire — For Approval
Sent to all 30 ACES members with the Welcome Email. Self-completion. Includes opt-in checkbox for protagonist interest.
ACTION REQUIRED: Munish to review and approve before Shefali sends. Estimated 15 minutes for participants to complete.
PART A — Starting Point
1. What is your background? (profession, industry, country)
2. Have you ever built an app or written code before?
3. On a scale of 1–10, how technical do you consider yourself?
4. What made you join the 100X program?
PART B — Your Why
1. What app are you trying to build, and why does it matter to you?
2. What is the thing you are most afraid of in this process?
3. What would it mean to you if this actually worked?
4. What does 'success' look like for you personally at the end of this?
PART C — Your Story
1. Is there a moment — in life or work — that led you here? Describe it.
2. What have you tried to build or create before that didn't work? What happened?
3. What do the people closest to you think about what you're doing?
PART D — Hardware & Filming Logistics
1. What device do you work on most? (laptop/desktop/tablet — model if you know it)
2. Do you have a decent webcam or external camera available?
3. Are you comfortable recording short clips of yourself working? (screen + face)
4. What is your available filming environment? (home office, café, shared space, other)
PART E — Documentary Opt-In
1. ☐ I am happy for my responses to be used as background context for the documentary.
2. ☐ I would like to be considered as one of five protagonists followed in depth.
(This means regular filming, Zoom interviews, and sharing your journey in real time.)
3. ☐ I do NOT wish to participate beyond this questionnaire. (No further contact.)

## Slide 14
PROTAGONIST SELECTION RUBRIC — COMPLETED | SHEFALI + MUNISH
Protagonist Selection Rubric
Used after questionnaire responses are in. Shefali and Munish score each respondent independently, then compare. Target shortlist: 8–10 candidates.
✓ DONE — Rubric created and distributed. Apply when questionnaire responses are in (M1 Week 2).
1
Specificity
Are their answers specific and personal — or generic and polished? Specific fear beats vague fear. A named person in the stakes question scores higher than 'my family'. Look for: proper nouns, exact moments, concrete consequences.
0–1 Generic answers. Could apply to anyone.
4–5 Answers that only this person could give.
2
Emotional Stakes
Is there something genuinely at risk for this person? Not just 'I want to learn' — something where failure would actually hurt. Look for: career pivots, personal proving grounds, people they need to show something to, things they've already failed at.
0–1 Learning goal. Safe aspiration.
4–5 Real cost to failing. Real person watching.
3
Contrast Potential
Does this person offer something different from the others already on the shortlist? The ensemble needs contrast — age, country, background, starting point, archetype. Score higher if they fill a gap. Score lower if they duplicate someone already shortlisted.
0–1 Similar to someone already on the list.
4–5 Fills a gap — age, country, archetype, starting point.
4
Surprise Factor
Did any answer genuinely surprise you? Did they subvert an assumption? Did they say something you didn't expect from someone in their situation? The wildcard protagonist lives here. Even one surprising answer is worth noting.
0–1 Answers landed as expected.
4–5 At least one answer stopped you. You didn't see it coming.
SCORING: Each criterion is scored 0–5. Maximum score: 20 · Shortlist target: score 14+ · Discuss 10–13 with Munish · Pass below 10

## Slide 15
PROTAGONIST ZOOM INTERVIEW QUESTIONS — FOR REVIEW AND APPROVAL BEFORE USE
Protagonist Zoom Interview Questions — For Approval
Used in Step 10: Zoom interviews with the 5 selected protagonists only. Shefali leads. Eddie as second. ~60 minutes per person.
ACTION REQUIRED: Munish to review and approve before interviews begin. These become the film's primary source material.
Opening — Identity & Starting Point
Before we start — how are you feeling right now, on the eve of building something you've never built before?
Tell me who you are. Not your job title — who you actually are, and how you ended up here.
What did the people in your life say when you told them what you were doing?
The Decision
What's the idea you're building, and where did it come from? Was there a specific moment?
What have you tried to build or create in the past that didn't work? What happened, and what did you do with that?
What do you believe that most people around you don't? About technology, about yourself, about what's possible?
Doubt & Pressure
What's the thing you're most afraid of in this process? Not the practical fear — the deeper one.
Is there a moment you can think of when you almost stopped? What kept you going?
Who is this for? Is there a specific person — real or imagined — whose life this would change?
Stakes & Closing
What would it mean — really mean — to you if this worked? And what would it mean if it didn't?
Six months from now, what do you hope you can say about this experience?
Is there anything nobody has asked you yet — about this, about you — that you wish they would?
Interview notes: Shefali leads all questions. Eddie holds space — observes, does not redirect. No rigid order — follow the person. Record with consent.

## Slide 16
GITHUB SETUP GUIDE — FOR THE TEAM
GitHub — How We Use It
GitHub is where all production documents live. The README is the team's shared pulse. Updated every Friday by each workstream owner.
5 Things You Need to Be Able to Do
1
Open the repo in a browser
Go to github.com → find the Zero to Hero repo → bookmark it.
2
Read the README
The README is on the front page of the repo. This is your weekly status update.
3
Edit your section of the README
Click the pencil icon. Find your workstream section. Update your 3 lines. Click 'Commit changes'.
4
Upload a file
Drag and drop your file into the right folder. Add a commit message. Click 'Commit changes'.
5
You will NOT break anything
GitHub keeps a full history. Every change can be undone. There is no deleting by accident.
Your Friday README Update — 3 Lines
STATUS:
On track / At risk / Blocked
THIS WEEK:
One sentence on what happened
NEXT WEEK:
One sentence on what's coming
Repo Folder Structure
📁 FROM-ZERO-TO-APP/ (root)
📁 01-PARTICIPANTS/ → one folder per person
📁 02-WHATSAPP-ARCHIVE/ → screenshots (Hansh)
📁 03-STORY-BIBLE/ → all versions (Shefali)
📁 04-SELECTS/ → Eddie's selects by week
📁 05-EDIT/ → all cut versions
📁 06-DELIVERY/ → final Netflix package
📁 07-PRODUCTION-DOCS/ → RACI, Gantt, budget
📄 README.md → team status (updated Fridays)
FILE NAMING RULE: [FIRSTNAME-LASTNAME]_[W##]_[TYPE]_[YYYY-MM-DD].[ext] e.g. SHEFALI-MODY_W03_SELF-SHOT_2025-03-17.mp4 — No spaces. Ever.